Fine Art Subject Guide Bibliography Refresh – 2026

|  | January / February | March | April | May | June |
| --- | --- | --- | --- | --- | --- |
| Review survey responses | Grace |  |  |  |  |
| Expand scope and elements of plan | Grace |  |  |  |  |
| Review Stakeholder feedback | Grace + Fine Art Librarians |  |  |  |  |
| Re-Communicate to academic teams – invite reading lists | Grace + Fine Art Librarians |  |  |  |  |
| Add materials from other bibliographies as available and fill gaps in Bibliography | Grace – CHE MA padlet The Edit, +++ |  |  |  |  |
| Investigate ‘nesting’ or stacked formats And / or additional ‘Starting Research’ introductory more visual carousel based page |  | Grace |  |  |  |
| Re-launch with ‘nesting’ / stacked format if possible |  |  |  | Grace | Grace |
| Launch ‘Starting Research’ themed carousels page |  | Grace Build and Select | Grace Select | Grace Finalise |  |
| Provide Moodle content for courses: Phase 1: Y1 intro Y2 Starting Research Y3 Unit 9.2 Phase2: All units |  |  |  |  | Grace – July - Sept |
| Review other H.E. libraries similar lists for themes and / or resources |  |  |  | Grace | Grace |
| Highlight libguides ownership and succession planning issue to SMT | Grace |  |  |  |  |
| Biannual review and additions / edits |  |  |  |  | Grace + Fine Art Librarians |